## Sprint_3
Project	Story	Task	Start (NOV 26)	Day 7	Day 6	Day 5	Day 4	Day 3	Day 2	Day 1 (DEC 3)
Unity	Story 1	Finish Ray Caster	4	0	1	0	0	4	0	0
Unity	Story 1	Get Sound Object Placement working	5	0	0	0	0	1	2	2
Unity	Story 1	Research file I/O with Unity	2	1	1	0	0	0	0	0
Unity	Story 1	Implement File I/O, get reads working	2	0	0	2	0	0	0	0

Ideal – Remaining effort in Ideal work hours			13	12	10	8	6	4	2	0
Actual – Remaining effort in Ideal work hours			13	12	10	8	8	3	1	-1
Burn Down Chart
Tasks
Days

## theBigOne
Project	Story	Task	Start (DEC 4)	Day 7	Day 6	Day 5	Day 4	Day 3	Day 2	Day 1 (DEC 11)
Unity	Story 1	Fix Sound Placement	4	1	1	1	4	4	0	0
Unity	Story 1	Implement Monster	4	0	0	0.5	0	4	0	0
Unity	Story 1	Add Exit Object	2	0	0	0	0	0	0	0
Unity	Story 1	Add SFX	3	0	1	0	0	0	1	0
Unity	Story 1	Add Unit Testing	7	0	1	0	1	4	0	0
Unity	Story 1	Make Presentation	4	0	0	0	0	4	2	0

Ideal – Remaining effort in Ideal work hours			24	20.5	17	13.5	10	6.5	3	0
Actual – Remaining effort in Ideal work hours			24	23	20	18.5	13.5	-2.5	-5.5	-5.5
Burn Down Chart
Tasks
Days